## Sheet1
Task Name | Start Date | End Date
Secure PET bottle source | 2023-01-09 | 2023-01-20 | 2023-01-09 | 2023-01-20
Determine regrind methodology | 2023-01-11 | 2023-01-19 | 2023-01-11 | 2023-01-19
Run NEXTRUCAD Simulations | 2023-01-23 | 2023-02-06 | 2023-01-23 | 2023-02-06
Run DSC on PET regrind flakes | 2023-01-25 | 2023-01-26 | 2023-01-25 | 2023-01-26
Take apart Filabot EX2 for analysis | 2023-02-01 | 2023-02-02 | 2023-02-01 | 2023-02-02
Run regrind flakes through Filabot EX2 | 2023-02-22 | 2023-02-24 | 2023-02-22 | 2023-02-24
Create pellets from bottle strips | 2023-03-01 | 2023-03-08 | 2023-03-01 | 2023-03-08
Determine screw parameters | 2023-02-06 | 2023-02-09 | 2023-02-06 | 2023-02-09
CAD extruder in Fusion 360 | 2023-02-06 | 2023-03-20 | 2023-02-06 | 2023-03-01
Order custom extruder parts | 2023-02-09 | 2023-03-31 | 2023-02-09 | 2023-02-11
Order generic extruder parts | 2023-03-01 | 2023-04-10 | 2023-03-01 | 2023-03-10
Assemble extruder | 2023-04-15 | 2023-04-18 | 2023-03-20 | 2023-04-03
|  |  | 2023-04-03 | 2023-04-07
|  |  | 2023-04-03 | 2023-04-07
|  |  | 2023-04-03 | 2023-04-07
3D Print different shapes to assess printing abilities | 2023-04-18 | 2023-04-19 | 2023-04-04 | 2023-04-08
Perform materials testing on prints | 2023-04-18 | 2023-04-19 | 2023-04-10 | 2023-04-12
Task Name | Start Date | Task duration
Secure PET bottle source | 0 | 11
Determine regrind methodology | 2 | 8
Run NEXTRUCAD Simulations | 14 | 14
Run DSC on PET regrind flakes | 16 | 1
Take apart Filabot EX2 for analysis | 23 | 1
Run regrind flakes through Filabot EX2 | 44 | 2
Create pellets from bottle strips | 51 | 7
Determine screw parameters | 28 | 3
CAD extruder in Fusion 360 | 28 | 42
Order custom extruder parts | 31 | 50
Order generic extruder parts | 51 | 40
Assemble extruder | 96 | 3
3D Print different shapes to assess printing abilities | 99 | 1
Perform materials testing on prints | 99 | 1